## 2026
|  | Project Name | Local Sponsor | Consultant | Anticipated Bid Solicitation Date | Anticipated Construction Commencement | Fill R- Monuments | Sand Source | Anticipate Cubic Yardage | Expected Dredge/Equipment Type | Approximate Min and Max Water Depths of Dredge Operation | Approximate Distance from Source to Discharge | Known Environmental Windows or other Project Limitations | Notes
1 | NE | South Ponte Vedra FEMA Cat G Project | St Johns County | First Line Coastal | 2026-02-01 | 2026-05-01 | R-76 to R-102.5 | Offshore | 1,000,000 cy | Hopper | 40' to 53' | 9.5 Miles | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls and dune walkovers throughout the project footprint
2 | SW | Doctors Pass Dredge | Collier County, Andy Miller | H&M | Bid due March 1 '26 | March 20, '26 | R-58A to R-59 | Doctors Pass | 35000 | Cutter | 7-13' | 1000' | Shorebird 2/15, Sea turtles 4/15
3 | SW | Manasota Key | Charlotte County | CEC | Mar. 2026 | Nov. 2026 | R1-R15 | Offshore | 400,000 cy | Hopper / Cutter | 20' to 45' | 4 Miles | Nov. through April only. | Rock revetments and Seawalls at ~60% of upland properties
4 | SW | Knight-Don Pedro Island | Charlotte County | CEC | Mar. 2026 | Nov. 2026 | R29-R40 | Offshore | 400,000 cy | Hopper / Cutter | 20' to 45' | 4 Miles | Shorebird protection and non-injurious deterrents from Mar 1 to Aug 31
5 | SW | Coquina Beach Idalia Restoration Project (FEMA Project #740969 DR-4734, P/W # 805) | Manatee County | Coastal Protection Engeneering | Jun/Jul-26 | 2026-08-01 | R-33 to R-41 | Longboat Pass Navigation Channel | 63,450 cy | Cutterhead | -8' to -30' | ~3000 ft | N/A. Permits allow construction in sea turtle nesting and shorebird breeding seasons. | Groins in fill location. FEMA status: funds obligated and PW approved.
6 | SW | Naples Renourishment | Collier County, Andy Miller | APTIM | July '26 | Nov. 2026 | R-58 to R-79 | Stewart Mine | 250000 | Truck Haul | N/A | N/A | N/A
7 | SE | IWW Broward Reach I | Florida Inland Navigation District (FIND) | Taylor Engineering | Summer 2026 | Fall 2026 |  | IWW | 35000 |  | 6'to 12' | 3-5 miles | Pre and post seagrass surveys to be completed | Upland Placement MSA 726 Exchange Club Park, Pompano Beach, FL
8 | SE | Bathtub Beach/Sailfish Point Beach Nourishment Project | Martin County BOCC | FOTH-Olsen | 2026-08-01 | 2027-01-01 | R-34 to R-40 | St. Lucie Inlet IB, Sailfish Point Channel | 200,000-300,000cy | Cutter | 5' to 18' | ~1 Mile | Nov. through April only. Required pipeline corridors. | These two projects will most likely be bid as one project by MC.
9 | SE | St. Lucie Inlet O&M | Martin County BOCC | GBA | 2026-08-01 | 2027-01-01 | R-45 to R-55 | St. Lucie Inlet Channel, IB and Transition Area | 400,000cy | Cutter | 5' to 18' | ~1 Mile to 2.5 Miles | Nov. through April only. Required pipeline cooridors.
10 | SE | SLWI Sand Trap Expansion | Palm Beach County ERM Reubin Bishop 561-233-2519 | Coastal Protection Engineering Dylan Nestler 904-806-7098 | 2026-08-01 | Nov. 2026 | NA | SLWI sand trap | 48,000 cy | Mechanical | 10' - 20' | 10 miles | Lake Worth Lagoon disposal area.
11 | SE | NCCSPP Segment 2 | Palm Beach County ERM Hailey Wilson 561-233-2465 | Foth Olsen Steve Howard (904) 717-8367 | 2026-08-01 | Nov. 2026 | R-19 to R-26 | Jupiter Borrow Area | 234,000 cy | Trailing Suction Hopper Dredge | 60' to 70' | 2.5 miles | Derelict cable in borrow area - survey in progress for quantity availability
12 | SE | NCCSPP Segment 3 | Palm Beach County ERM Hailey Wilson 561-233-2465 | Foth Olsen Steve Howard (904) 717-8367 | 2026-08-01 | Nov. 2026 | R-26 to R-38 | Jupiter Borrow Area | ~600,000 cy | Trailing Suction Hopper Dredge | 60' to 70' | 5.0 miles | Derelict cable in borrow area - survey in progress for quantity availability
15 | SW | Coquina Beach Debby/Helene/Milton Restoration Project (DR-4806, DR-4828, DR-4834) | Manatee County | Coastal Protection Engeneering | Aug/Sep-26 | 2026-11-01 | R-33 to R-41 | Passage Key Ebb Shoal | 91,300 cy (requested) | Cutterhead | -8' to -24' | ~6 miles | N/A. Permits allow construction in sea turtle nesting and shorebird breeding seasons. | Groins in fill location. FEMA status: currently under review.
13 | SW | South Marco Renourishment | Collier County, Andy Miller | H&M | Oct. '26 | Jan. '27 | R-143 to R-148 | Stewart Mine | 75000 | Truck Haul | N/A | N/A | N/A
14 | SE | 2027 Jupiter Inlet Sand Trap Dredging | Jupiter Inlet District | Taylor Engineering - Ken Craig | 2026-11-01 | 2027-02-01 | PBC R-14 to R-16 | Interior inlet sand trap | 80,000 cy | hydraulic suction cutterhead dredge | -8 to -21' | ~0.5 mi | All equipment demobilized from beach by April 30, turbidity monitoring at dredge and placement locations, sea turtle nest monitoring
16 | SW | South Siesta Key Beach | Sarasota County, Joseph Kraus | TBD | 2026 | Spring or Fall 2027 | R-67 to R-77 | Upland or Offshore | Storm damage repair with the possibility of maintenance sand up to ±500,000 CY (est.) | Truck Haul or Hopper Dredge | -38.0' NAVD to -47.0" NAVD if hopper dredge | 6.2 to 8.7 miles if hopper dredge | Preferred window outside of sea turtle nesting season. Screening is potentially required if offshore sand is used. Possible Spring Break conflicts if truck haul. The project design will need to consider the county's intention to keep Midnight Pass open, as stated in line 6 below. | Significant delays processing FEMA storm damage repair claims.
17 | SW | Manasota Key Beach | Sarasota County, Joseph Kraus | TBD | 2026 | Spring or Fall 2027 | R-171 to R-183 | Upland | Storm damage repair plus maintenance sand up to ±250,000 CY (est.) | Truck Haul or Hopper Dredge | -32.0' NAVD to -46.0' NAVD if hopper dredge | 2.65 to 6.8 miles if hopper dredge | Preferred window outside of sea turtle nesting season. Possible Spring Break conflicts if truck haul. May need new sand search if offshore borrow area. Conflict with FEMA EHP and USFWS regarding CBRS unit. | 2020 Restoration project done jointly with Charlotte County. There may be insufficient offshore sand for full renourshment of entire project area.
18 | NE | Ponte Vedra Beach FEMA Cat G Project | St Johns County | TBD | Mid 2027 | Mid 2027 | R-1 to R-46.2 | Offshore | 800,000 CY | Hopper | TBD | 3 Miles | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls, Geotubes, and dune walkovers throughout the project footprint
19 | CE | Volusia County Shoals to Shores | Volusia County, Jessica Fentress and Niles Cyzycki | Taylor Engineering, Wendy Laurent | 2027 | 2027 | TBD b/w R-66 to R-118 | Ponce Inlet Flood Shoals | 1,700,000 cy | Cutter | 0' to 15' | TBD, min 6 mi | TBD- will depend on shorebirds, turtle nesting, right whales, etc.
20 | SW | Midnight Pass | Sarasota County, Joseph Kraus | Currently working with Geosyntec Consultants | Unk. | Unk. | R-073 to R-083 | Inlet | TBD | TBD | TBD | <1.0 Mile | A project scope is currently undetermined, though the County's intent is to "Keep Midnight Pass Open." The inlet is located within a USFWS CBRS Unit. | Hurricanes Helene and Milton in 2024 reopened the inlet, which had been closed since 1983. The county intends to maintain the open pass. The adjacent beaches, South Siesta Key Beach and North Casey Beach, are critically eroded.
21 | SW | Wiggins Pass Dredge | Collier County, Andy Miller | H&M | Bid due Jan. 19, '26 | Feb. 15, '26 | R-18 to R-20 | Wiggins Pas | 75000 | Cutter | 7-13' | 1500' | Shorebird 2/15, Sea turtles 4/15
22 | CE | Sebastian Inlet Sand Trap Dredging and Beach Placement Project (Phase 2) | Sebastian Inlet District | AtkinsRealis | 2024-08-01 | 2025-12-25 | R-3.5 - R-12 | Sand Trap/Nav. Channel | 200,000 CY | Cutter | 5' to 17' | ~2.5 Miles | Constructon Nov. through April only. Project located within Sebastian Inlet State Park. 150 meter downcurrent turbidity mixing zone at the dredge site (inlet). 150 meter alongshore turbidity mixing zone at nourishment site (beach). Marine turtle nesting season May 1 to October 31. Shorebird nesting season March 15 to September 1 | McLarty Treasure Museum Revetment on beach (~R-10.5)
23 | NW | St. Joseph Peninsula Beach Nourishment and Coastal Structures Project | Gulf County | MRD Associates, Inc. | 2025-06-01 | 2026-03-01 | R-100 to R-105.8 | Offshore | 830,000 cy | Hopper | 30' to 35' | ~9 miles | Oct 1 through June 1 only | eight (8) submerged breakwaters in initial fill template

## 2025
1 | SE | 2025 Jupiter Inlet Sand Trap Dredging | Jupiter Inlet District | Taylor Engineering | 2025-01-01 | 2025-03-01 | R-14 - R-16 (Palm Beach Co. R-mons) | Jupiter Inlet sand trap | 80,000 cy | hydraulic suction cutterhead | 21.5' | 3,500' | Beach placemtn operations and equipment demobilized from beach by April 30 | pay in the cut, clean medium sand
2 | SW | Captiva Island | CEPD | APTIM, Nicole Sharp | 2024-01-01 | May 1 - July 1, 2025 | R-84 to R-109 | Offshore | 1182000 | Hopper | Approx. 40' | 7 miles | Sea turtle monitoring and nest relocations required during nesting season; no restricted pipeline corridors | n/a
3 | SW | Erosion Control Project | Charlotte | Coastal Engineering Consultants | January 2025 Bid Opening | Mar. 2025 | R18-R21, R22-R24 | Inlet | 270,000 cy | Cutter | 8' to 14' | < 1 Mile | No work on Manastoa Key after May 1 | Breach at R17 north of fill, Terminal Groin at R21 fill terminus
4 | NW | Pensacola Beach Renourishment | Santa Rosa Island Authority, Juan Lemos | Foth ¦ Olsen, Krista Egan | 2025-02-01 | 2025-11-01 | R-107.5 to R-150.5 | Offshore | 1,600,000 cy | Hopper | 60' to 80' | 4 miles | No work in the summer | n/a
5 | E | Dune Restoration south of Ponce Inlet | Volusia County, Niles Cyzycki | Intera, Mike Trudnak | 2025-02-01 | 2025-05-01 | R-160 to R-190 | Florida Inland Navigation District MSA 434-S DMMA | 500,000 CY | Cutter | NA | 3 to 8 Miles | N/A. | Hydraulic offloading of the MSA 434 - S DMMA onto the beach in New Smyrna Beach. The DMMA currently holds approximatley 500,000 cubic yards of beach compatible sand.
6 | NW | Western Destin Beach Restoration | Okaloosa County. Alex Fogg Natural Resources Chief | Taylor Engineering, Duncan Greer | 2025-03-01 | 2025-11-01 | R-17 - R-20.5 R-23.5 - R25.5 | Offshore Regionally Permitted Borrow Area | 150,600 cy | Cutter / Hopper | 40' - 50' | ~ 4 miles | Nov. through April only. Required pipeline cooridors. 500 meter turbidity mixing zone at beach. Screening required. | FEMA Category G Hurricane Sally
7 | SW | Pinellas County Beach Renourishment | Pinellas County | APTIM, Jacob Rice | April. 2025 | May. 2025 | R-56 to R-66; R-71 to R-108A; R-126 to R-128A; R-136 to R-142; R-144 to R-146 | John's Pass, Blind Pass, Pass-A-Grille, and Egmont Shoals Borrow Areas | 2,200,000 cy | Cutterhead; Clamshell | 10' to 30' | From ~0.25 to ~21 nautical miles | Required pipeline cooridors. Hardbottom with 300 foot buffer required. Sea turtle and smalltooth sawfish conditions. | Reourishment may be advertised as two projects, dependent on timeline and constructability.
8 | NE | Flagler County Dune and Beach Restoration Project - Reach II | Flagler County, Ansley Wren-Key | Foth ¦ Olsen LLC | 2025-05-01 | 2025-07-01 | R45 - R77 | offshore | 1,800,000 cy | hopper | 50'-65' | ~ 12 miles | MEC screening | seawalls at ~30% of properties; numerous public and private walkovers
9 | NW | St. Joseph Peninsula Beach Renourishment and Coastal Structures Project | Gulf County | MRD Associates, Inc. | May/Jun-25 | 2025-08-01 | R-100 to R-105.8 | Offshore | 800,000 cy | Hopper | 30' to 40' | ~9 miles | Currently restricted from construction during peak marine turtle nesting season | Multiple seawalls/upland retaining walls within landward limits of fill, includes construciton of eight submerged breakwaters
10 | CE | Vero Beach Sector 5 | Indian River County, Eric Charest | APTIM, Nicole Sharp | 2025-06-01 | 2025-11-01 | R70-R86 | Upland | 150,000 cy | N/A | N/A | N/A | November through April construction timeframe only. Not currently permitted for offshore sand source. | Some seawalls, some easements not currently executed - properties not participating. Project slated to address Hurricanes Ian and Nicole sand losses and background erosion experienced since out last nourishment event.
11 | NE | South Ponte Vedra FEMA Cat G Project | St Johns County | First Line Coastal | 2025-08-01 | 2025-12-01 | R-76 to R-102.5 | Offshore | 1,000,000 cy | Hopper | 40' to 53' | 9.5 Miles | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls and dune walkovers throughout the project footprint
12 | SW | Coquina Beach Restoration Project (FEMA Project) | Manatee County | Coastal Protection Engeneering | Aug/Sep-25 | 2025-11-01 | R-33 to R-41 | Longboat Pass | 74,800 cy (requested) 63,450 cy (revised by FEMA, R-33 to R-36 removed because it overlaps with taper of Federal project) | Cutterhead | -13' | ~3000 ft | N/A. Permits allow construction in sea turtle nesting and shorebird breeding seasons. | Further investigation needed to determine volume of sand available for dredging in the borrow source. Groins in fill location. FEMA status: currently under EHP review
13 | SE | South Lake Worth Inlet Sand Trap Expansion | Palm Beach County. Contact Andy Studt | Coastal Protection Engineering, Tom Pierro | Sept. 2025 | Jan. 2026 | Inshore Only | SLWI Sand Trap Expansion | ~115,000 cy | Hard Rock Excavator(s)/Punch | 5' to 18' | 3.5 to 10 miles | No blasting. Hard rock excavation anticipated, contractor with demonstrated experience required. Beneficial reuse/placement of dredge material in LWL. | Lateral expansion and deepening of existing interior SLWI Sand Trap.
14 | SW | South Siesta Key Beach | Sarasota County, Joseph Kraus | TBD | Late 2025 | Spring or Fall 2026 | R-67 to R-77 | Upland or Offshore | Storm damage repair plus maintenance sand up to ±500,000 CY | Truck Haul or Hopper Dredge | -38.0' NAVD to -47.0" NAVD | 6.2 to 8.7 miles if hopper dredge | Preferred window outside of sea turtle nesting season. Screening potentially required if offshore sand used. Possible Spring Break conflicts if truck haul.
15 | SW | Manasota Key Beach | Sarasota County, Joseph Kraus | TBD | Late 2025 | Spring or Fall 2027 | R-171 to R-183 | Upland | Storm damage repair plus maintenance sand up to ±250,000 CY | Truck Haul | N/A | N/A | Preferred window outside of sea turtle nesting season. Possible Spring Break conflicts if truck haul.
16 | SE | 2026 Jupiter Inlet Sand Trap Dredging | Jupiter Inlet District | Taylor Engineering | 2026-01-01 | 2026-03-01 | R-14 - R-16 (Palm Beach Co. R-mons) | Jupiter Inlet sand trap | 80,000 cy | hydraulic suction cutterhead | 21.5' | 3,500' | Beach placemtn operations and equipment demobilized from beach by April 30 | pay in the cut, clean medium sand
17 | SE | North County Comprehensive Shore Protection Project Segments 2 and 3. | Palm Beach County. Contact Andy Studt | Foth/Olsen, Steve Howard | Mar. 2026 | Nov. 2026 | R-19 to R-38 | Offshore borrow area | ~234,000 cy (Segment 2) ~ 610,000 cy (Segment 3) | Trailing Suction Hopper Dredge | 64' to 72' | 2.3 to 5.7 miles | Nov. through March with additional approval required for April work. 200m by 1000 m turbidity mixing zone. Vibratory screening required. | Screened shell content ≥1% of dredge volume; offsite hauling of screened shell required.
18 | NE | Ponte Vedra Beach FEMA Cat G Project | St Johns County | TBD | TBD | 2026 | R-1 to R-46.2 | Offshore/Upland | TBD | Hopper/Truck Haul | TBD | 4.5 Mile | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls, Geotubes, and dune walkovers throughout the project footprint